# Commercials and Engagement Model

TASCO Insurance × VETC Growth Platform — Business & Product

iorta TechNXT

Version 1.0 · 07 October 2026

Table of Contents

| Document | Version | Date | Owner | Status |
| --- | --- | --- | --- | --- |
| Commercials and Engagement Model | 1.0 | 07 October 2026 | iorta TechNXT — Engagement Lead | Issued for submission |

iorta TechNXT proposal to TASCO Insurance × VETC · Classification: Client Confidential

This document sets out the commercial detail behind the proposal Proposal for the TASCO Motor Insurance Growth Platform (reference ITN-TASCO-2026-001), and the figures in both documents are the same. Prices are in US dollars, with Vietnamese dong shown at USD 1 = VND 26,000 (assumption C-01). Prices exclude VAT and any foreign contractor tax. Business-case figures are illustrative. References such as "doc 01" point to the companion documents listed in the Business and Product Documentation index (00-index.pdf).

## 1. Engagement summary

| Item | Proposal |
| --- | --- |
| Objective | Take the existing TASCO Growth Platform to a live pilot integrated with TASCO's core system and VETC's channels, within TASCO's MVP budget of USD 100,000; then, if the pilot succeeds, scale to the full VETC base and run it as a managed service |
| Starting point | A working platform: 80 API routes, staff console for 13 roles and customer app, rules-driven lead intelligence, journeys, voice-bot dialogue engine, sales and issuance, partner API, rules governance, audit and privacy controls, 238 automated tests and a live UAT environment |
| Phases | 0 Discovery (2 weeks) → 1 MVP (11 weeks to go-live, then 4 weeks of hypercare) → 2 Scale (about 6 months, optional) → 3 Run (managed service, optional) |
| MVP price | USD 94,800 fixed (≈ VND 2.46 bn). A change reserve of USD 5,200 is held by TASCO, so the total is USD 100,000. |
| Commercial options | A. Fixed-price MVP (recommended) · B. Lower fixed MVP price plus a capped per-policy technology service fee |
| Indicative 3-year TCO (full scale) | ≈ USD 669,558 (≈ VND 17.41 bn), including the scale phase, managed service, enhancement pool and cloud infrastructure; excludes usage fees and TASCO/VETC internal costs |

## 2. Phases, scope and deliverables

| Phase | Scope | Key deliverables | Exit gate |
| --- | --- | --- | --- |
| 0 Discovery | TASCO core integration path (catalogue, rating, issuance); data mapping (VETC accounts, partner lists, TASCO policy book); legal confirmations; integration contracts; pilot design with a control group; voice-vendor selection support | Discovery report; signed integration specifications; pilot plan; baselined KPIs (doc 01 §11) | Steering committee sign-off |
| 1 MVP | Production adapters for TASCO core (catalogue sync, live rating, bind and issue, daily policy extract), VETC (data load, tag activation, app web view, push, wallet), Zalo ZNS, SMS brandname and one voice vendor; one partner on the API; branding and configuration; hardening; SIT, UAT and security testing; pilot of 50,000–100,000 vehicles | Production release; runbooks; trained users; pilot dashboard; security test report; test-case workbook | UAT sign-off; go-live; 4 weeks of hypercare within service levels |
| 2 Scale (optional) | Full 6 M base; VETC SSO; Zalo mini app; live VETC event feed; inspection booking; fleet portal; data-warehouse feed; claims integration; score calibration; A/B testing; further partners | Scaled platform; experimentation framework; fleet portal | KPI review against the base case |
| 3 Run (optional) | Managed service: L2/L3 support, monitoring, security patching, rule-change support, monthly releases | Monthly service report; quarterly business review | Service levels met |

## 3. Team composition and effort

### 3.1 MVP (Phases 0 and 1)

Effort in person-days.

| Role | Discovery | Build | Test and go-live | Hypercare | Total |
| --- | --- | --- | --- | --- | --- |
| Engagement manager | 5 | 20 | 7.5 | 2 | 34.5 |
| Solution architect | 10 | 20 | 3.75 |  | 33.75 |
| Business analyst and insurance SME | 10 | 40 | 15 | 5 | 70 |
| UX and conversation designer | 5 | 10 |  |  | 15 |
| Senior engineer (integration lead) | 5 | 40 | 15 | 10 | 70 |
| Engineers (backend and frontend) |  | 80 | 15 | 10 | 105 |
| QA engineer |  | 40 | 22.5 |  | 62.5 |
| DevSecOps engineer |  | 20 | 7.5 | 5 | 32.5 |
| Total | 35 | 270 | 86.25 | 32 | 423.25 |
| Duration | 2 weeks | 8 weeks | 3 weeks | 4 weeks | 17 weeks |

The MVP team is small because the platform already exists. Effort goes to integration, data onboarding, configuration, hardening and the pilot, not to building the console, the customer app or the business logic.

### 3.2 Phase 2 (Scale) and Phase 3 (Run)

| Phase | Basis |
| --- | --- |
| Phase 2 Scale | About 4.5 FTE for about 26 weeks; capped at 590 person-days |
| Phase 3 Run | Managed service at a fixed monthly fee (§4.3), including 40 hours of minor enhancements a month; larger changes are drawn from the enhancement pool at the rate card |

### 3.3 Client-side commitments (not priced)

| TASCO / VETC role | Commitment |
| --- | --- |
| TASCO product owner | About 0.5 FTE in Phases 0–2 |
| TASCO core system lead | Interface specifications, sandbox, support during integration testing |
| VETC data and integration lead | About 0.5 FTE in Phases 0–1 |
| Underwriting, finance and legal reviewers | Sign-off on tariffs, commission caps, wording, consent and PDP within 5 business days |
| Telesales team lead and agents | UAT and pilot participation |
| IT security | Security requirements, access approvals, penetration-test scope |

## 4. Commercial models and prices

### 4.1 MVP price build-up

| Item | USD |
| --- | --- |
| Delivery effort at the standard rate card (423.25 person-days, §3.1 and §4.4) | 107,485 |
| Accelerator credit for reuse of the existing platform | (12,685) |
| MVP fixed price (Option A) | 94,800 |
| Perpetual licence for TASCO's use, including source code | Included |
| Up to three on-site visits to Hà Nội | Included |
| 90-day warranty from go-live | Included |
| Change reserve held by TASCO (used only with TASCO approval) | 5,200 |
| Total within the MVP budget | 100,000 |

### 4.2 Option B: shared outcome

| Component | Basis | Price |
| --- | --- | --- |
| MVP fixed price | Same scope and timeline as Option A | USD 74,800 |
| Technology service fee | VND 10,000 per policy issued digitally through the platform (own channels and partner API) for 12 months after go-live | Capped at USD 50,000 |
| Phases 2 and 3 | As Option A | As Option A |

Illustrative fee at pilot scale. Option B costs TASCO more than Option A only if more than 52,000 policies are issued through the platform in the 12 months after go-live: USD 20,000 × VND 26,000 ÷ VND 10,000 = 52,000 policies. That is well above the expected pilot volume, so the option mainly suits a fast roll-out.

Legal note (confirm with TASCO legal). The fee must be structured as a technology service fee per processed transaction, not as an insurance commission or brokerage fee. Under the Law on Insurance Business 08/2022/QH15, commission may be paid only to licensed intermediaries. The fee must not be passed on to customers or affect the premium in any way.

### 4.3 After the MVP (optional)

| Service | Basis | Price (USD) |
| --- | --- | --- |
| Phase 2 Scale | Time and materials, about six months, capped at 590 person-days | Up to 147,500 |
| Phase 3 Managed service | Monthly, 12-month initial term, includes 40 hours of minor enhancements a month | 6,900 per month |
| Enhancement pool | Drawn down at the rate card by work order | 48,000 per year (budgetary) |

### 4.4 Rate card

| Role | Daily rate (USD) |
| --- | --- |
| Engagement manager | 380 |
| Solution architect | 360 |
| Business analyst and insurance SME | 260 |
| Senior engineer or DevSecOps engineer | 260 |
| UX and conversation designer | 230 |
| Engineer | 210 |
| QA engineer | 190 |

### 4.5 Option comparison

| Criterion | Option A | Option B |
| --- | --- | --- |
| Budget certainty for TASCO | High: fixed price | Medium: fee varies with volume, capped |
| Shared risk on outcomes | Low | Higher |
| Upfront cost | USD 94,800 | USD 74,800 |
| Administration | Low | Quarterly reconciliation from the platform's audited order records |
| Best when | The budget is approved and certainty matters | TASCO prefers to link cost to results |

## 5. Payment milestones

| Milestone | Trigger and acceptance evidence | Share | Option A (USD) | Option B (USD) |
| --- | --- | --- | --- | --- |
| M0 Mobilisation | Contract signed; team onboarded (week 0) | 15% | 14,220 | 11,220 |
| M1 Discovery complete | Discovery report, integration specifications and pilot design signed off (week 2) | 15% | 14,220 | 11,220 |
| M2 Integrated build | End-to-end demonstration on sandboxes: core rating and issuance, wallet debit, Zalo message, voice call (week 10) | 25% | 23,700 | 18,700 |
| M3 Acceptance | UAT signed off; no open critical or high security findings (week 13) | 25% | 23,700 | 18,700 |
| M4 Pilot live | Go-live plus 4 weeks of hypercare within service levels (week 17) | 20% | 18,960 | 14,960 |
| Total |  | 100% | 94,800 | 74,800 |

Invoices are payable within 30 days. Phase 2 is invoiced monthly in arrears against timesheets, up to the cap. Phase 3 is invoiced monthly in advance. Option B fees are invoiced quarterly from platform transaction reports.

## 6. Run-cost estimate (cloud infrastructure in Vietnam)

The estimate assumes managed Kubernetes and managed PostgreSQL from a cloud provider in Vietnam (NFR-030), for example Viettel IDC, VNG Cloud or FPT Cloud, or Tasco group's private cloud. The provider is chosen in Phase 0, and TASCO pays for infrastructure directly.

| Component | Pilot (USD per month) | Full scale (USD per month) | Sizing basis |
| --- | --- | --- | --- |
| Application nodes (Kubernetes) | 450 | 900 | 3 → 6 nodes of 4 vCPU / 16 GB |
| PostgreSQL (HA primary and standby) | 600 | 1,400 | 8 vCPU / 32 GB → 16 vCPU / 64 GB plus a reporting replica |
| Backups and object storage (35-day PITR) | 80 | 150 | NFR-051 – NFR-053 |
| Load balancer, WAF and egress | 150 | 250 | Edge rate limiting |
| Observability (metrics, logs, traces) | 150 | 300 | NFR-047 – NFR-049 |
| Non-production environments | 200 | 350 | Synthetic or masked data only (NFR-033) |
| Secrets, key management and miscellaneous | 20 | 50 | Key rotation (NFR-023) |
| Total | ≈ 1,650 | ≈ 3,400 |  |

Usage-based costs (paid by TASCO/VETC to providers, not in the TCO). Rates come from config/rules/costs.json, and volumes are the doc 01 base case at full scale.

| Item | Unit cost (VND) | Base-case volume | Annual (VND) |
| --- | --- | --- | --- |
| Voice-AI minutes | 1,500 per minute × 1.6 minutes | 497,250 calls | ≈ 1.19 bn |
| Zalo ZNS and SMS | 300 / 700 per message | 5 sends × 2.8 M profiles (mix) | ≈ 2.24 bn |
| App push | 0 | — | 0 |
| Telesales (internal staff time) | 6,000 per minute × 4.5 minutes | 50,000 calls | ≈ 1.35 bn |

## 7. Total cost of ownership (Option A, full-scale path, indicative)

Year 1 runs from November 2026 to October 2027. The scale phase starts only after a successful pilot read-out.

| USD | Year 1 | Year 2 | Year 3 | Three years |
| --- | --- | --- | --- | --- |
| MVP (fixed price) | 94,800 |  |  | 94,800 |
| Scale phase (capped) | 147,500 |  |  | 147,500 |
| Managed service | 55,200 | 82,800 | 85,284 | 223,284 |
| Enhancement pool (optional) |  | 48,000 | 48,000 | 96,000 |
| Cloud infrastructure | 25,150 | 40,800 | 42,024 | 107,974 |
| Total | 322,650 | 171,600 | 175,308 | 669,558 |
| ≈ VND | 8.39 bn | 4.46 bn | 4.56 bn | 17.41 bn |

Year 3 includes a 3% increase on the managed service and infrastructure. Pilot-only path: if TASCO keeps the platform at pilot scale without Phase 2, the year-1 cost is about USD 168,150 (MVP, 8 months of managed service and 11 months of pilot infrastructure).

Context against the business case (doc 01 §12, illustrative). In the base case, the year-2 platform cost (USD 0.17 M ≈ VND 4.46 bn) is about 5% of total premium through the platform (VND 86.3 bn). The voice bot's saving on qualifying calls alone, about VND 12.2 bn a year against human telesales, exceeds the annual platform cost. The pilot's control group must confirm incrementality before scale-up (doc 01 §12.4).

## 8. Governance and ways of working

| Forum | Cadence | Participants | Purpose |
| --- | --- | --- | --- |
| Steering committee | Monthly | TASCO and VETC executives, iorta engagement lead | Scope, budget, KPI review, phase gates |
| Product council | Fortnightly | TASCO product owner, VETC lead, iorta analyst and architect | Backlog priority, rule-change requests |
| Sprint review | Every 2 weeks | Product owner, key users | Demonstration against doc 04 acceptance criteria |
| Change control | As needed | Product owner, engagement lead | Scope changes and their impact on price and timeline |
| Compliance checkpoint | Per release | Compliance approver (PS-05) | Wording, consent, PDP, audit evidence |

Delivery approach. Two-week sprints. The definition of done is: acceptance criteria met, tests at NFR-042 thresholds, lint clean, OpenAPI updated, and security checks passed. After go-live, business rule changes go through the rules studio (maker-checker) and do not need a release.

Managed-service service levels (Phase 3). Business hours are 08:00–17:30 Vietnam time, Monday to Friday.

| Priority | Example | Response | Restore / workaround |
| --- | --- | --- | --- |
| P1 | Purchase path down; data breach suspected | 30 min (24×7) | 4 h |
| P2 | Journey run failing; one integration down | 2 business hours | 1 business day |
| P3 | Non-critical defect | Next business day | Next release |
| P4 | Enhancement or question | 3 business days | Planned |

## 9. Assumptions

| ID | Assumption |
| --- | --- |
| C-01 | FX USD 1 = VND 26,000. Prices are quoted in USD, and invoices can be issued in USD or VND at a rate agreed at contract. |
| C-02 | The rate card in §4.4 applies to change requests, Phase 2 and the enhancement pool. |
| C-03 | 1 FTE-week = 5 person-days; 1 month = 21 person-days. |
| C-04 | TASCO provides core interface documentation (catalogue, rating, issuance) and a sandbox, or agrees the interim rating path, by the end of week 2; VETC provides sandboxes for wallet, push and the app web view by the same date; production credentials are available by week 10. |
| C-05 | One voice-AI vendor (SIP plus Vietnamese ASR/TTS) is selected in Phase 0 and contracted directly by TASCO/VETC. Per-minute costs are pass-through. |
| C-06 | The pilot cohort is 50,000–100,000 vehicles in 1–2 provinces, with a randomised control group. |
| C-07 | TASCO legal confirms tariff, commission caps, contact policy, PDP basis and data residency in Phase 0. Delays move milestones day for day. |
| C-08 | Hosting is in Vietnam on a managed Kubernetes and PostgreSQL platform chosen in Phase 0, and TASCO pays for it directly. |
| C-09 | The existing codebase is the baseline. The open engineering notes in doc 05 that affect the MVP scope are closed in Phase 1; the rest in Phase 2. |
| C-10 | User acceptance is against doc 04 acceptance criteria for in-scope stories. |
| C-11 | The console is in English and Vietnamese, and the customer app is in Vietnamese. Customer wording is written or approved by TASCO/VETC. |

## 10. Exclusions

- Licences and usage fees of third-party services: voice-AI minutes, Zalo OA/ZNS, SMS brandname, push providers and cloud infrastructure.

- Changes inside TASCO's core system, the VETC app's native code, the VETC wallet or the VETC identity provider, beyond consuming their APIs.

- Claims adjudication, reserving, reinsurance and finance-system integration (accounting entries, VAT e-invoicing).

- Independent penetration testing by a third party (recommended; indicatively USD 6,000–10,000 in Vietnam), certification or audit fees.

- Migration of historical TASCO policy archives beyond the expiry-relevant fields.

- Legal, actuarial or regulatory advice. The platform encodes TASCO's decisions; it does not make them.

- On-premise hardware, and 24×7 coverage for P2–P4 (available on request).

- Marketing spend, call-centre staffing and customer-communication costs.

## 11. Key commercial risks

| Risk | Mitigation |
| --- | --- |
| TASCO core rating API not available in time | Interim path: approved tariff tables in the platform with core re-rating at issue; decided in week 2 |
| Integration sandboxes late | Simulated adapters already exist, so build continues; milestone dates move day for day by agreement |
| Legal confirmations late (PDP, wording, loyalty) | Conservative defaults in rules; features gated (legalStatus, referral.enabled = false) |
| Scope growth during the MVP | Clear MVP boundary; change control; USD 5,200 reserve under TASCO's control |
| Outcome-fee disputes (Option B) | Fee computed from the platform's audited, hash-chained order records |