# Go-Live and Hypercare Plan — TASCO Growth Platform

TASCO Insurance × VETC Growth Platform — Operations

iorta TechNXT

Version 1.0 · 07 October 2026

Table of Contents

| Document | Version | Date | Owner | Status |
| --- | --- | --- | --- | --- |
| Go-Live and Hypercare Plan | 1.0 | 07 October 2026 | iorta TechNXT Delivery Lead (cutover manager); TASCO Product Owner (business go-live owner) | Issued for submission |

| Item | Value |
| --- | --- |
| Decision body | Steering Committee (go/no-go G3); CAB (production changes) |
| Dates (indicative, per the Project Plan) | G3 go/no-go Friday 22 January 2027 · pilot soft launch Monday 25 January 2027 (low volume, Hà Nội + TP.HCM) · Tết change freeze 01–14 February 2027 · pilot full volume Monday 15 February 2027 · G4 pilot review 12 March 2027 · W1 nationwide 29 March 2027 · W2 partner API 26 April 2027 |
| Related | Production Readiness Checklist · Runbook and Support Guide · Release and Change Management · DR and BCP |

## 1. Go-live approach

This is a greenfield launch. No legacy system is replaced; current renewal reminders continue in parallel as the control group. Exposure grows in controlled steps, using levers that already exist in the platform:

| Lever | How | Granularity |
| --- | --- | --- |
| Which vehicles exist in the platform | Only the pilot cohort is ingested (POST /api/data/ingest / batch load) | Cohort-level |
| Who is targeted by journeys | Journey audience (JSON Logic) in the journeys rule set: add {"in":[{"var":"region"},["Hà Nội","TP. Hồ Chí Minh"]]} and expiry and category filters. Changes go through maker-checker | Region, category, days to expiry, confidence, tier |
| Which products and channels are on sale | products rule set: status and channels[] per product; bundles[].status | Product × channel |
| Which benefits are shown | benefits rule set legalStatus (only approved reach customers) and available (false keeps roadmap items such as auto_renew and fleet_dashboard staff-only); referral.enabled. Loyalty points stay pending legal review and are never promised to customers | Item |
| Contact intensity | contact_policy caps; manual voice campaigns with limit | Global |
| Entry points | VETC app banner/feature flag (VETC side); Zalo OA menu; assisted sales by telesales (quote sent to the customer's app, never paid by staff); partner keys issued only at W2 | Channel |
| Kill switch | SOP-07: suspend the journeys CronJob; marketing cap 0 via rules | Global |

Percentage roll-out ("10 % of the base") is not expressible today: no fact gives a stable random bucket (KI-24). Use region, category or expiry filters, or the cohort loaded, until a cohortBucket fact is added. The pilot A/B control group (project plan) needs that fact, or a control list excluded at load time; decide this at G3.

## 2. Go / no-go criteria (G3)

| # | Criterion | Evidence | Owner |
| --- | --- | --- | --- |
| G-1 | Every P1 item of the readiness checklist is Done or Waived by the SteerCo | Checklist | Delivery Lead |
| G-2 | UAT accepted (overall + every persona); compliance scenarios passed without waiver | UAT sign-off sheet | TASCO Business Owner |
| G-3 | Security sign-off (pen test: no open critical/high) | CISO memo | TASCO CISO |
| G-4 | Compliance and legal sign-offs: content inventory, contact policy, tariffs, ZNS templates approved by Zalo, PDP/DPIA | Memos | Compliance / Legal / DPO |
| G-5 | Sev 1 and compliance known issues fixed and regression-tested: KI-01 (seed guard), KI-02 (saga compensation), KI-09 (voice campaign contact policy), KI-28 (no in-memory store in production) and KI-33 (at override only in demo mode) are fixed in release 1.0.0; their regression cases (TC-080, TC-134, TC-135, TC-159, TC-162) pass on the release tag; open Sev 2 items (KI-04, KI-13, KI-18) fixed or waived with a date | Results workbook + KI register | Dev lead |
| G-6 | Partners ready in PROD: VETC wallet + SSO + app deep link + push, TASCO core issuance, Zalo OA/ZNS, SMS brandname, voice vendor; DR egress allow-listed | Partner confirmations | Integration lead |
| G-7 | Operational readiness: on-call live, runbook tabletop done, dashboards and alerts live, synthetics green for 48 h in PROD | Ops sign-off | L2 lead |
| G-8 | Dress rehearsal of cutover and rollback completed in PREPROD within the planned times | Rehearsal report | Cutover manager |
| G-9 | Pilot cohort data loaded in PREPROD with real extracts; counts reconcile | Load report | Data steward |
| G-10 | No open Sev 1/Sev 2 defects (or Sev 2 waived with a fix date before 15 February) | Defect report | QA Lead |

Decision rule: all of G-1 to G-10 met → GO. One or more unmet with a credible fix within 48 h → GO with conditions (soft launch delayed to the fix). Otherwise NO-GO, with the next decision point set by the SteerCo; the Tết freeze means the next possible soft launch is 15 February.

## 3. Cutover plan (T-minus schedule)

T0 = Monday 25 January 2027, 08:15 ICT (first scheduled journey run: CronJob tasco-growth-journeys at 01:15 UTC).

| When | Activity | Owner | Exit check |
| --- | --- | --- | --- |
| T−21 d (Monday 4 January) | PROD and DR infrastructure provisioned from IaC; PostgreSQL HA + PITR + cross-region replica; KMS keys created; monitoring stack, dashboards and alerts deployed | SRE, DBA | PRC-DR-01, PRC-OPS-01 |
| T−14 d (Monday 11 January) | Release candidate v1.0.0-rc.N tagged = UAT build; feature freeze (fixes only); provisional CAB approval for the go-live change | Release manager | CAB minutes |
| T−10 d (Friday 15 January) | Partner PROD connectivity: allow-lists (PROD + DR egress), credentials in the vault; Zalo template IDs mapped; SMS brandname live; voice vendor numbers | Integration lead | Connectivity test per partner (no customer traffic) |
| T−7 d (Monday 18 January) | PROD secrets loaded (JWT_SECRET, DATA_KEYS with DATA_KEY_ACTIVE, BLIND_INDEX_KEY, DATABASE_URL, METRICS_TOKEN); migration Job (npm run migrate); rule sets seeded (npm run job -- rules); verify no demo users and no DEMO_* variables; named users created (each must change the initial password); MFA self-enrolment session for privileged users | SRE, Admin | /health/ready → store:"postgres"; GET /api/ops/status rule checksums recorded |
| T−5 d (Wednesday 20 January) | Dress rehearsal in PREPROD: full cutover + rollback, timed; DR-T1, DR-T2, DR-T7 | Cutover manager | Rehearsal report (G-8) |
| T−3 d (Friday 22 January) | G3 go/no-go (SteerCo 14:00); final release tag v1.0.0; CAB final approval | SteerCo, CAB | Signed decision |
| T−2 d (Saturday 23 January) 09:00–17:00 | Deploy v1.0.0 to PROD (migration Job → rollout); smoke tests (§3.1); journeys CronJob deployed suspended; load the soft-launch cohort (~20 k vehicles HN + HCM, car TNDS, expiry 15–60 days) in batches of ≤ 2,000; DQ review | SRE, Data steward | Counts reconcile (TC-112); reconciliation job clean |
| T−1 d (Sunday 24 January) 10:00 | POST /api/leads/recompute; journey audience rule restricted to the pilot regions approved (maker-checker); review the next day's due touchpoints (GET /api/touchpoints?status=scheduled) per journey/channel with campaign managers; voice campaign limits agreed (≤ 200 calls/day at soft launch) | Campaign manager, Compliance | Volume sign-off |
| T−1 d 18:00 | Final checkpoint (go/hold): synthetics green 24 h, no open Sev 1/2, on-call staffed, war room booked | Cutover manager | Recorded decision |
| T0 08:00 | War room open; dashboards D1–D5 on screen; VETC app entry point enabled (VETC) | All | — |
| T0 08:05 | Unsuspend the journeys CronJob before its 08:15 run (or run npm run job -- journeys manually inside the window for the first day); confirm the tasco-growth-relay CronJob is active | L2 | journey run complete log reviewed |
| T0 09:00–12:00 | Watch the first messages (sent/failed/blocked), first deep-link sessions, first orders end to end (wallet → TASCO core → certificate verify), first assisted sales (quote sent by an agent, paid by the customer in the app); first voice campaign (limit 50) at 10:00 | War room | First order verified via QR |
| T0 17:00 | Day-1 review (§5 KPIs); decide day-2 volume | PO | Minutes |
| T+1 … T+5 | Daily ramp per §4; hypercare routine | War room | — |

### 3.1 Smoke tests after any PROD deployment

- GET /health/ready → 200, store:"postgres", db:true on every pod.

- GET /api/meta → demoMode:false, correct version.

- GET /api/demo/totp/admin → 404.

- Staff login + MFA (named smoke account); GET /api/auth/me.

- GET /metrics without a token → 401.

- GET /api/ops/status: all integrations closed; rules[] checksums equal the change log; eventBacklog.dead_letter unchanged.

- GET /api/audit/verify → ok:true.

- Certificate verification for the synthetic test certificate (SYN-02).

- (Go-live day only) One real end-to-end purchase for an internal staff vehicle, paid by its owner as a customer in the VETC app, then a check of the certificate QR. Cancel or keep per the TASCO decision.

## 4. Pilot ramp-up

| Period | Scope (journeys/products) | Volume control | Gate to next step |
| --- | --- | --- | --- |
| 25–29 January (week 1) | Car TNDS renewal journey only; app push + ZNS; voice bot ≤ 200 calls/day; telesales squads HN/HCM | ~20 k vehicles loaded; audience = HN + HCM, expiry 15–60 days | Daily KPIs green; no compliance incident |
| 01–14 February (Tết freeze) | Run only: no deployments, no rule changes except emergency rollback (RB-10) or kill switch (SOP-07). Journeys continue at low volume; voice campaigns paused 5–14 February (holiday) | Same cohort | — |
| 15 February onwards | Full pilot volume: renewal + conquest + lapsed recovery; SMS fallback on | Load the rest of the cohort (100–200 k); voice ≤ 2,000 calls/day | Weekly pilot review |
| 12 March | G4: KPIs vs targets, unit economics (/api/dashboard/overview economics), no open regulatory issue | — | SteerCo decision on W1 |

## 5. Rollback plan

### 5.1 Triggers (any one → the Incident Commander proposes rollback; the PO and TASCO IT Head decide within 30 min)

| Trigger | Threshold |
| --- | --- |
| Compliance breach | Any marketing contact outside 08:00–20:00 ICT, any contact with a DNC customer, any customer message with banned wording, any call without consent |
| Money without cover | > 3 orders in a day with captured payment and no policy that are not refunded within 24 h; any confirmed double charge |
| Availability | Purchase path SLO-01 breached for > 2 h, or a Sev 1 not resolved within 4 h |
| Data integrity | Audit chain verification fails; wrong customer data shown to another customer |
| Partner instruction | VETC or TASCO core requests suspension |

### 5.2 Rollback levels

| Level | Action | Time to effect | Data impact |
| --- | --- | --- | --- |
| R1: Stop outbound contact | SOP-07: suspend the journeys CronJob; stop voice campaigns; marketing cap 0 via rules | Minutes | None |
| R2: Rule rollback | Maker-checker rollback of the faulty rule set (RB-10) | ~15 min (two people) | None |
| R3: Application rollback | Redeploy the previous image tag (kubectl rollout undo or re-apply the previous release manifest). Database migrations are forward-only and must be backward-compatible (expand/contract), so the previous version runs on the new schema | ≤ 15 min | None |
| R4: Close customer entry points | VETC disables the app banner/entry point; Zalo OA menu hidden; partner keys suspended (PATCH /api/partners/:id {status:"suspended"}) | ≤ 1 h (VETC release process) | None; in-flight quotes expire after 24 h |
| R5: Full withdrawal of the pilot | R1 + R4; platform stays up for servicing existing policies (certificate verification, FNOL, DSAR), which must never be switched off for customers who already bought | ≤ 2 h | Policies remain valid; reconciliation completes |
| R6: Data restore | Only for corruption: PITR per FO-2 (DR and BCP §6) | Hours | Writes after the restore point need reconciliation |

For the first go-live there is no previous application version. R3 is replaced by R1 + R4 (switch off exposure) while a hotfix is prepared.

## 6. Hypercare

### 6.1 Duration and organisation

| Wave | Hypercare window | Notes |
| --- | --- | --- |
| Pilot | 25 January → 12 March 2027 (≈ 6 weeks, spanning Tết at reduced intensity) | Extended because of the freeze and the low volume during Tết |
| W1 nationwide | 29 March → 23 April 2027 (4 weeks) | Volume ×20–30 versus pilot |
| W2 partner API | 26 April → 21 May 2027 (4 weeks) | Partner onboarding support |

| Element | Arrangement |
| --- | --- |
| War room | Physical (TASCO HQ Hà Nội) + virtual bridge; 08:00–20:00 ICT on weekdays in weeks 1–2, then virtual |
| Stand-ups | 08:00 ICT (overnight jobs, alerts, KPIs, plan) and 17:00 ICT (day review, decisions) |
| Staffing | iorta: tech lead, 2 developers, QA, SRE (L3 on-call 24×7); TASCO: PO, L2 support, compliance analyst, campaign manager, telesales supervisor; VETC: app/CS liaison |
| Change policy | Daily hotfix window 07:00 ICT (before the journey run) for Sev 1/2 fixes via the emergency CAB; rule changes only through maker-checker, with the PO's consent during hypercare |
| Defect SLAs | As the runbook severity matrix, with L3 engaged directly for Sev 1/2 |

### 6.2 Daily KPI pack (07:45 ICT, reviewed at the 08:00 stand-up)

| Area | KPI | Source | Threshold for action |
| --- | --- | --- | --- |
| Journeys | Touchpoints due / done / skipped / deferred / cancelled by journey and channel; skip reasons top 5 | journey run complete log, touchpoints | Skipped > 30 % (other than consent) → RB-07 |
| Messaging | Sent / failed / blocked by channel | messages_total | Blocked > 0 → Compliance (ALR-30) |
| Voice | Calls by outcome; plate-verification failure (plate_mismatch + unverified) %; opt-out % | voice_calls_total | Verification failure > 15 % (ASR quality); opt-out > 10 % |
| Telesales | Handoffs created / claimed / won / lost; open > 2 business hours | GET /api/handoffs, tasco_db_handoffs_open_older_than_2h | > 20 aged handoffs |
| Sales funnel | Quotes and orders by channel and journey; conversion; GWP; taps-to-certificate (VETC analytics) | quotes_total, orders_completed_total, dashboard | Conversion −50 % week-over-week |
| Integrity | issuance_failed_refunded, compensation_failed and payment_failed orders; reconciliation mismatches | orders_compensation_total, orders, GET /api/ops/jobs | Any → RB-11 (compensation_failed is Sev 1) |
| Data | New DQ issues by type; customer-confirmed expiries | GET /api/dq/issues, audit customer.expiry_declared | — |
| Reliability | SLOs (availability, p95), incidents by severity, alerts fired, dead letters | Dashboards D1–D3 | SLO burn > 50 % of weekly budget |
| Compliance | Contacts outside the window (SQL: must be 0), DNC contacts (0), complaints | RB-07 query, CS | Any → Sev 1 |
| Support | Tickets by tier and category; % resolved at L1/L2 | ITSM | L3 share > 30 % in week 3+ |

### 6.3 Hypercare exit criteria (per wave)

| # | Criterion |
| --- | --- |
| H-1 | No Sev 1 for 14 consecutive days and no open Sev 2 |
| H-2 | SLO-01 – SLO-04 met for the last 14 days |
| H-3 | Journeys complete inside the window daily for the last 10 business days |
| H-4 | Reconciliation clean (0 unexplained mismatches) for 10 consecutive days |
| H-5 | L2 resolves ≥ 80 % of tickets without L3; runbooks and KEDB updated with every new incident type |
| H-6 | Alert noise: < 5 non-actionable pages per week |
| H-7 | Open Sev 3 defects < 10, each with a planned release |
| H-8 | KT sessions for this wave's features completed (see the KT Plan, docs/delivery/kt-plan.pdf) |
| H-9 | Business Owner and TASCO IT Head sign the hypercare exit |

## 7. Transition to BAU

| Item | Hand-over to BAU |
| --- | --- |
| Support | L2 rota fully TASCO; L3 via the AMS contract with the severity SLAs from the runbook |
| Monitoring | Alert routing switched to TASCO on-call; dashboards owned by TASCO IT ops |
| Releases | Monthly release train via CAB (Release and Change Management); rule changes are a business-as-usual activity of TASCO rule authors and approvers |
| Knowledge | KT plan completion; runbook, SOPs and readiness evidence archived; open known issues with owners |
| Governance | Monthly service review (SLOs, incidents, capacity, KI burn-down); quarterly DR test reports; quarterly access review |